## Budget
Total
| Estimated Cost | Actual Cost | Variance
Cory
Jillian
Andrew S.
Bidhi
Nihat K.
Aneesha
Chenny
Total

## Gantt
| Estimated Time (hrs) | Prereq | Status/Time Spent | Key | Complete | Current Work | Planned
Cory Clairmont |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Coordinate other tl's needs | 2 | N/A | bar: Key 1 to Complete 2
2. Create sound need checklist | 2 | 1 | bar: Current Work 3 to Planned 4
3. Plan Enemy Design | 4 | 1 | bar: Current Work 3 to Planned 6
4. Coordinate Level Themes | 1 | 1,2 | bar: Planned 5
5. Coordinate Player Sounds | 2 | 1,2 | bar: Planned 5 to Planned 6
6. Coordinate Enemy Sounds | 2 | 1,3 | bar: Planned 7 to Planned 8
7. Source Sound effects | 2 | 5,6 | bar: Planned 9 to Planned 10
8. Source music | 2 | 4 | bar: Planned 6 to Planned 7
9. Design Enemy Movement | 4 | 3 | bar: Planned 7 to Planned 10
10. Help Progarm Enemys | 6 | 9 | bar: Planned 9 to Planned 14
11. Apply Sound To Enemies | 3 | 10,7 | bar: Planned 15 to Planned 17
12. Apply Themes to Levels | 2 | 8 | bar: Planned 8 to Planned 9
13. Apply Sounds to Player | 3 | 5,7 | bar: Planned 11 to Planned 12
14. Align music with scenes | 2 | 12 | bar: Planned 10 to Planned 11
15. Mixing Audio Levels | 3 | 11,12,13 | bar: Planned 18 to Planned 20
16. Validate Audio Triggers | 3 | 12 | bar: Planned 18 to Planned 22
17. Debugging/Testing | 4 | 16, 15 | bar: Planned 23 to Planned 26
18. Installation/Finalizing | 3 | 17 | bar: Planned 27 to Planned 29
19. Stress Test | 2 | 18 | bar: Planned 30 to Planned 31
Jillian Jabbes
Research References and Plan | 2 | bar: Key 1 to Complete 2
Setup Base Object Hiearchy and Components | 3 | 1 | bar: Current Work 3 to Planned 5
Setup Player Controller Script | 4 | 2 | bar: Planned 6 to Planned 9
Inputs and Movement Logic | 6 | 3 | bar: Planned 10 to Planned 15
Integrate Physics & Collision | 3 | 2,3,4 | bar: Planned 16 to Planned 18
Playtest + Adjustments | 1 | 5 | bar: Planned 19
Combat Logic | 5 | 5 | bar: Planned 19 to Planned 23
Player Hitbox | 3 | 5,7 | bar: Planned 24 to Planned 26
Work with Weapon Specialist | 6 | 8 | bar: Planned 27 to Planned 32
Finalize Combat | 2 | 9 | bar: Planned 33 to Planned 34
Define Player Stats + Inventory | 3 | 3,7 | bar: Planned 24 to Planned 26
Work with UI/HUD Specialist | 4 | 11 | bar: Planned 27 to Planned 30
Implement Player Sprite Animation | 7 | 2,4,10 | bar: Planned 35 to Planned 41
Final Playtest for Player Object | 2 | 14 | bar: Planned 42 to Planned 43
Help Program Bosses + Collab | 7 | 11 | bar: Planned 27 to Planned 33
Help Implement Game Graphics | 8 | 15 | bar: Planned 44 to Planned 51
Playtesting + Debugging | 6 | 16 | bar: Planned 52 to Planned 57
Andrew Sorensen
Bidhi Paudel
Research and Planning | 4 | bar: Key 1 to Planned 4
Coordinate with Enemy Specialist | 6 | 1 | bar: Planned 5 to Planned 10
Define Weapon Attributes | 8 | 1 | bar: Planned 5 to Planned 12
Create Weapon Art and Animations | 8 | 3 | bar: Planned 13 to Planned 20
Set Up Shooting Mechanics | 4 | 3,4 | bar: Planned 13 to Planned 16
Design Powerups & Effects | 8 | 3 | bar: Planned 13 to Planned 20
Place Weapon and Powerups in Game Levels | 4 | 4,6 | bar: Planned 21 to Planned 24
Implement Collision and Hit Detection | 4 | 5 | bar: Planned 21 to Planned 24
Integrate with Player Controls | 3 | 7 | bar: Planned 25 to Planned 27
Test Weapon and Powerups | 3 | 8,9 | bar: Planned 28 to Planned 30
Adjust and Balance Gameplay | 4 | 10 | bar: Planned 31 to Planned 34
Final Testing and Polishing | 4 | 11 | bar: Planned 35 to Planned 38
Nihat K Polat
Begin the level design process | 7 | N/A | bar: Key 1 to Planned 7
Create and set up backgrounds | 7 | 1 | bar: Planned 8 to Planned 14
Arrange tiles to form the map | 8 | 1 | bar: Planned 8 to Planned 15
Add physics component | 4 | 2, 3 | bar: Planned 15 to Planned 18
Add interactive elements | 6 | 4 | bar: Planned 19 to Planned 24
Add objectives | 6 | 4 | bar: Planned 19 to Planned 24
Create cutscenes | 5 | 5, 6 | bar: Planned 25 to Planned 29
Implement checkpoints | 6 | 7 | bar: Planned 30 to Planned 35
Documentation | 4 | N/A | bar: Planned 34 to Planned 37
Debugging and testing | 6 | 8, 9 | bar: Planned 38 to Planned 43
Installation and finalize | 4 | 10 | bar: Planned 44 to Planned 46
Aneesha Shrestha
Cheny Amadike
Conceptualize HUD graphic ideas | 2 | - | bar: Key 1 to Complete 2
Main Menu UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
Pause Menu UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
Game Over Screen UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
HUD Design and Implementation | 6 | 1 | bar: Current Work 3 to Planned 8
UI Animations, Effects and Transitions | 5 | 2,3,4,5 | bar: Planned 9 to Planned 13
User Input and Navigation Integration | 5 | 6 | bar: Planned 14 to Planned 18
UI Sound Effect Integration | 4 | 6 | bar: Planned 19 to Planned 22
Debugging and testing | 6 | 7,8 | bar: Planned 23 to Planned 28
Final Integration and Polishing | 4 | 9 | bar: Planned 29 to Planned 32

## TL Deliverables
TL1 Deliverables | TL2 Deliverables | TL3 Deliverables | TL4 Deliverables | TL5 Deliverables | TL6 Deliverables
Due Date: | Due Date: | Due Date: | Due Date: | Due Date: | Due Date:
Deliverables should be on GitHub by midnight on Due Date and marked with a check (✓) mark under.