## Budget
| Total |  |  |  | Coding and Design |  |  |  | Meetings |  |  |  | Overhead
| Estimated Cost | Actual Cost | Variance |  | Estimated Cost | Actual Cost | Variance |  | Estimated Cost | Actual Cost | Variance |  | Estimated Cost | Actual Cost | Variance
Cory | 8200 | 2500 | $TBD | Cory | 5200 | 1400 | $TBD | Cory | 3000 | 1100 | $TBD | Cory
Jillian | 10200 | 3100 | $TBD | Jillian | 7200 | 1900 | $TBD | Jillian | 3000 | 1200 | $TBD | Jillian
Andrew S. | 8300 | 1600 | $TBD | Andrew S. | 5300 | 600 | $TBD | Andrew S. | 3000 | 1000 | $TBD | Andrew S.
Bidhi | 9000 | 1300 | $TBD | Bidhi | 6000 | 400 | $TBD | Bidhi | 3000 | 900 | $TBD | Bidhi
Nihat K. | 9300 | 1900 | $TBD | Nihat K. | 6300 | 600 | $TBD | Nihat K. | 3000 | 1300 | $TBD | Nihat K.
Aneesha | 8500 | 4400 | $TBD | Aneesha | 5500 | 2200 | $TBD | Aneesha | 3000 | 1200 | $TBD | Aneesha
Chenny | 8800 | 3600 | $TBD | Chenny | 5800 | 2300 | $TBD | Chenny | 3000 | 1300 | $TBD | Chenny
Total | 62300 | 17400 | $TBD | Total | 43100 | 9400 | $TBD | Total | 21000 | 8000 | $TBD | Total

## Gantt
| Estimated Time (hrs) | Prereq | Status/Time Spent | Key | Complete | Current Work | Planned
Cory Clairmont |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Coordinate other tl's needs | 2 | N/A | bar: Key 1 to Complete 2
2. Create sound need checklist | 2 | 1 | bar: Current Work 3 to Planned 4
3. Plan Enemy Design | 4 | 1 | bar: Current Work 3 to Planned 6
4. Coordinate Level Themes | 1 | 1,2 | bar: Planned 5
5. Coordinate Player Sounds | 2 | 1,2 | bar: Planned 5 to Planned 6
6. Coordinate Enemy Sounds | 2 | 1,3 | bar: Planned 7 to Planned 8
7. Source Sound effects | 2 | 5,6 | bar: Planned 9 to Planned 10
8. Source music | 2 | 4 | bar: Planned 6 to Planned 7
9. Design Enemy Movement | 4 | 3 | bar: Planned 7 to Planned 10
10. Help Progarm Enemys | 6 | 9 | bar: Planned 9 to Planned 14
11. Apply Sound To Enemies | 3 | 10,7 | bar: Planned 15 to Planned 17
12. Apply Themes to Levels | 2 | 8 | bar: Planned 8 to Planned 9
13. Apply Sounds to Player | 3 | 5,7 | bar: Planned 11 to Planned 12
14. Align music with scenes | 2 | 12 | bar: Planned 10 to Planned 11
15. Mixing Audio Levels | 3 | 11,12,13 | bar: Planned 18 to Planned 20
16. Validate Audio Triggers | 3 | 12 | bar: Planned 18 to Planned 22
17. Debugging/Testing | 4 | 16, 15 | bar: Planned 23 to Planned 26
18. Installation/Finalizing | 3 | 17 | bar: Planned 27 to Planned 29
19. Stress Test | 2 | 18 | bar: Planned 30 to Planned 31
Jillian Jabbes
1. Research References and Plan | 2 | N/A | bar: Key 1 to Complete 2
2. Setup Base Object Hiearchy and Components | 3 | 1 | bar: Current Work 3 to Planned 5
3. Setup Player Controller Script | 4 | 2 | bar: Planned 6 to Planned 9
4. Inputs and Movement Logic | 6 | 3 | bar: Planned 10 to Planned 15
5. Integrate Physics & Collision | 3 | 2,3,4 | bar: Planned 16 to Planned 18
6. Playtest + Adjustments | 1 | 5 | bar: Planned 19
7. Combat Logic | 5 | 5 | bar: Planned 19 to Planned 23
8. Player Hitbox | 3 | 5,7 | bar: Planned 24 to Planned 26
9. Work with Weapon Specialist | 6 | 8 | bar: Planned 27 to Planned 32
10. Finalize Combat | 2 | 9 | bar: Planned 33 to Planned 34
11. Define Player Stats | 3 | 3,7 | bar: Planned 24 to Planned 26
12. Work with UI/HUD Specialist | 4 | 11 | bar: Planned 27 to Planned 30
13. Implement Player Sprite Animation | 7 | 2,4,10 | bar: Planned 35 to Planned 41
14. Final Playtest for Player Object | 2 | 14 | bar: Planned 42 to Planned 43
15. Help Program Bosses + Collab | 7 | 11 | bar: Planned 27 to Planned 33
16. Help Implement Game Graphics | 8 | 15 | bar: Planned 44 to Planned 51
17. Playtesting + Debugging | 6 | 16 | bar: Planned 52 to Planned 57
Andrew Sorensen
1. First Boss Level Loader | 2 | N/A | bar: Key 1 to Complete 2
2. First Boss Object/Collision | 2 | 1 | bar: Current Work 3 to Planned 4
3. First Boss Stats | 1 | 2 | bar: Planned 5
4. First Boss Movement | 4 | 2 | bar: Planned 5 to Planned 8
5. First Boss Attack/Training | 4 | 3, 4 | bar: Planned 9 to Planned 12
6. First Boss Sprites | 2 | 4, 5 | bar: Planned 13 to Planned 14
7. First Boss Testing | 4 | 5 | bar: Planned 13 to Planned 16
8. Second Boss Level Loader | 2 | 7 | bar: Planned 17 to Planned 18
9. Second Boss Object/Collision | 2 | 8 | bar: Planned 19 to Planned 20
10. Second Boss Stats | 1 | 9 | bar: Planned 21
11. Second Boss Movement | 4 | 9 | bar: Planned 21 to Planned 24
12. Second Boss Attack/Training | 4 | 10, 11 | bar: Planned 25 to Planned 28
13. Second Boss Sprites | 2 | 11, 12 | bar: Planned 29 to Planned 30
14. Second Boss Testing | 4 | 12 | bar: Planned 29 to Planned 32
15. Third Boss Level Loader | 2 | 14 | bar: Planned 33 to Planned 34
16. Third Boss Object/Collision | 2 | 15 | bar: Planned 35 to Planned 36
17. Third Boss Stats | 1 | 16 | bar: Planned 37
19. Third Boss Attack/Training | 4 | 17, 18 | bar: Planned 38 to Planned 41
20. Third Boss Sprites | 2 | 18, 19 | bar: Planned 42 to Planned 43
21. Third Boss Testing | 4 | 20 | bar: Planned 42 to Planned 45
Bidhi Paudel
1. Research and Planning | 4 | N/A | bar: Key 1 to Planned 4
2. Coordinate with Enemy Specialist | 6 | 1 | bar: Planned 5 to Planned 10
3. Define Weapon Attributes | 8 | 1 | bar: Planned 5 to Planned 12
4. Create Weapon Art and Animations | 8 | 3 | bar: Planned 13 to Planned 20
5. Set Up Shooting Mechanics | 4 | 3,4 | bar: Planned 13 to Planned 16
6. Design Powerups & Effects | 8 | 3 | bar: Planned 13 to Planned 20
7. Place Weapon and Powerups in Game Levels | 4 | 4,6 | bar: Planned 21 to Planned 24
8. Implement Collision and Hit Detection | 4 | 5 | bar: Planned 21 to Planned 24
9. Integrate with Player Controls | 3 | 7 | bar: Planned 25 to Planned 27
10. Test Weapon and Powerups | 3 | 8,9 | bar: Planned 28 to Planned 30
11. Adjust and Balance Gameplay | 4 | 10 | bar: Planned 31 to Planned 34
12. Final Testing and Polishing | 4 | 11 | bar: Planned 35 to Planned 38
Nihat K Polat
1. Begin the level design process | 7 | N/A | bar: Key 1 to Planned 7
2. Create and set up backgrounds | 7 | 1 | bar: Planned 8 to Planned 14
3. Arrange tiles to form the map | 8 | 1 | bar: Planned 8 to Planned 15
4. Add physics component | 4 | 2, 3 | bar: Planned 15 to Planned 18
5. Add interactive elements | 6 | 4 | bar: Planned 19 to Planned 24
6. Add objectives | 6 | 4 | bar: Planned 19 to Planned 24
7. Create cutscenes | 5 | 5, 6 | bar: Planned 25 to Planned 29
8. Implement checkpoints | 6 | 7 | bar: Planned 30 to Planned 35
9. Documentation | 4 | N/A | bar: Planned 34 to Planned 37
10. Debugging and testing | 6 | N/A | bar: Key 1 to Planned 14
11. Installation and finalize | 4 | 9, 10 | bar: Planned 38 to Planned 40
Aneesha Shrestha
1. Requirement Collection | 3 | N/A | bar: Key 1
2. Sprite Design | 4 | 1 | bar: Complete 2 to Planned 5
3. Movement Design | 4 | 1 | bar: Complete 2 to Planned 5
4. Attack Design | 4 | 1 | bar: Complete 2 to Planned 5
5. Minimum Viable Product | 10 | 1. 3. 4 | bar: Planned 6 to Planned 13
6. Assigning Sprites to movement | 2 | 2, 5 | bar: Planned 6 to Planned 7
7. Testing on blank backgrounds | 2 | 5,6 | bar: Planned 14 to Planned 15
8. Testing with main character | 4 | 7 | bar: Planned 16 to Planned 19
9. Installation | 2 | 8 | bar: Planned 20 to Planned 21
10. Requirement Collection for AI | 2 | 0 | bar: Planned 20 to Planned 21
11. Building AI runner | 10 | 10 | bar: Planned 22 to Planned 31
12. Creating AI escape sequence | 1 | 11 | bar: Planned 31
13. Testing and debugging AI on all levels | 5 | 12 | bar: Planned 32 to Planned 36
14. Installation/Finalization | 2 | 13 | bar: Planned 37 to Planned 38
Cheny Amadike
1. Conceptualize HUD graphic ideas | 2 | N/A | bar: Key 1 to Complete 2
2. Main Menu UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
3. Pause Menu UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
4. Game Over Screen UI Development | 5 | 1 | bar: Current Work 3 to Planned 7
5. HUD Design and Implementation | 15 | 1 | bar: Current Work 3 to Planned 15
6. UI Animations, Effects, Graphics | 5 | 2,3,4,5 | bar: Planned 16 to Planned 20
7. User Input and Navigation Integration | 5 | 6 | bar: Planned 21 to Planned 25
8. UI Sound Effect Integration | 6 | 6 | bar: Planned 26 to Planned 31
9. Debugging and testing | 6 | 7,8 | bar: Planned 32 to Planned 37
10. Final Integration and Polishing | 4 | 9 | bar: Planned 38 to Planned 41

## TL Deliverables
TL1 Deliverables | TL2 Deliverables | TL3 Deliverables | TL4 Deliverables | TL5 Deliverables | TL6 Deliverables
Due Date: | Due Date: | Due Date: | Due Date: | Due Date: | Due Date:
Deliverables should be on GitHub by midnight on Due Date and marked with a check (✓) mark under.

## Meetings
| Jan. 24 | Jan. 27 | Feb. 3 | Feb. 10 | Feb. 24 | Mar. 24
| First Meeting | Weekly Meeting | Weekly Meeting | SA Presentation Prep | MVP Prep | Weekly Meeting
Hours | 1 | 2 | 2 | 3 | 4 | 1
Cory | 1 | 2 | 2 | 3 | 2 | 1
Jillian | 1 | 2 | 2 | 3 | 4 | - | 2
Andrew S | 1 | 2 | 2 | 3 | 2 | - | 3
Bidhi | 1 | 2 | 2 | 3 | 1 | - | 4
Nihat K | 1 | 2 | 2 | 3 | 4 | 1 | 1
Aneesha | 1 | 2 | 2 | 3 | 3 | 1
Chenny | 1 | 2 | 2 | 3 | 4 | 1
Total | 7 | 14 | 14 | 21 | 20 | 4